06. Pre-Start Assurance and Meeting Record Expanded Checklist Confirm that the contract, site, safety, programme and client operation are ready before work starts.

PROJECT DETAILS

| Project title | Enter the controlled project title used on approvals, appointments and contract documents. ________________________________________________________________ | Project reference | Use the organisation’s project number or another unique reference that will remain stable throughout the project. ________________________________________________________________ |
| --- | --- | --- | --- |
| Client / organisation | Enter the legal or operational client organisation responsible for the project. ________________________________________________________________ | Site / building | Identify the building, site, floor, room or package clearly enough for another reviewer to understand the project boundary. ________________________________________________________________ |
| Prepared by | Name the person coordinating this review. Technical or legal answers should still be confirmed by the appropriately appointed adviser. ________________________________________________________________ | Review date | Enter the date of this review. Update it when the checklist is formally revisited. ________________________________________________________________ |

Document version: 1.0  |  22 July 2026

HOW TO USE THIS CHECKLIST Open the file early and keep it live. Select a status for every line, record the evidence or decision, and give every action an owner and due date. Use N/A only where the matter genuinely does not apply and explain why. A checklist supports client governance; it does not replace project-specific professional, legal, technical, safety or procurement advice. Status: [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] Not applicable

EXPANDED WORKING CHECKLIST

Complete each item with the project team. Attach or identify supporting evidence where appropriate.

A1 ¦ CONTRACT AND AUTHORITY. Confirm the building contract or written order is executed. Guidance: Check parties, scope, sum, dates, amendments, signatures and any conditions precedent before possession or work begins.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

A2 ¦ CONTRACT AND AUTHORITY. Confirm the contractor’s insurance evidence. Guidance: Record policies, limits, expiry dates, project-specific requirements and any outstanding endorsements.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

A3 ¦ CONTRACT AND AUTHORITY. Confirm bonds, warranties, guarantees and parent-company security. Guidance: Check required forms, execution status, beneficiaries and delivery dates.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

A4 ¦ CONTRACT AND AUTHORITY. Identify who may issue instructions, approve changes and certify payments. Guidance: Ensure the client team and contractor understand the contractual communication route.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

A5 ¦ CONTRACT AND AUTHORITY. Confirm the contract sum, pricing documents and agreed clarifications. Guidance: The final contract baseline should match the tender recommendation and approved post-tender position.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

B1 ¦ PROGRAMME AND POSSESSION. Agree the possession or access date and conditions. Guidance: Distinguish early access, mobilisation, enabling work and full possession. Record areas excluded or shared.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

B2 ¦ PROGRAMME AND POSSESSION. Review the detailed construction programme. Guidance: Include design, procurement, approvals, phases, shutdowns, testing, commissioning, handover and client fit-out.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

B3 ¦ PROGRAMME AND POSSESSION. Confirm contract completion, milestones and restricted dates. Guidance: Record sectional completion, events, examinations, seasonal constraints and dates when work cannot occur.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

B4 ¦ PROGRAMME AND POSSESSION. Create a client decision and information schedule. Guidance: Identify what the contractor needs, who must provide it and the latest date that avoids delay.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

B5 ¦ PROGRAMME AND POSSESSION. Identify long-lead items and early design approvals. Guidance: Record submittal dates, review periods, samples, procurement status and recovery action for risk items.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

C1 ¦ CDM AND SAFETY. Confirm client, principal designer and principal contractor appointments. Guidance: Check roles are in writing and that cooperation, coordination and information-sharing arrangements are clear.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

C2 ¦ CDM AND SAFETY. Review the Construction Phase Plan before work starts. Guidance: The plan should be project-specific, proportionate and address the actual site, work and client constraints.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

C3 ¦ CDM AND SAFETY. Confirm pre-construction information has been provided and acknowledged. Guidance: Include surveys, hazards, existing services, asbestos, access, operations and client rules.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

C4 ¦ CDM AND SAFETY. Confirm welfare will be available from the start. Guidance: Check location, capacity, servicing, accessibility, water, toilets, washing, changing, rest and drying arrangements.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

C5 ¦ CDM AND SAFETY. Confirm site induction, competence and subcontractor controls. Guidance: Record who manages induction, permits, supervision and verification of specialist competence.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

C6 ¦ CDM AND SAFETY. Confirm F10 notification status where applicable. Guidance: Check current statutory requirements and retain the notification or reason it is not required.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

C7 ¦ CDM AND SAFETY. Agree emergency and incident arrangements. Guidance: Cover first aid, fire, rescue, spill, utility strike, security incident, serious defect and out-of-hours escalation.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

C8 ¦ CDM AND SAFETY. Confirm asbestos, hazardous materials and permit arrangements. Guidance: Define survey boundaries, intrusive-work controls, discoveries, stop-work action and client permit systems.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

D1 ¦ SITE LOGISTICS AND ACCESS. Approve the site logistics plan. Guidance: Show boundaries, compounds, welfare, deliveries, waste, storage, lifting, pedestrian routes and emergency access.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

D2 ¦ SITE LOGISTICS AND ACCESS. Agree access hours, keys, passes, parking and security. Guidance: Record controlled areas, escorts, safeguarding, background checks and out-of-hours arrangements.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

D3 ¦ SITE LOGISTICS AND ACCESS. Agree delivery and material-handling arrangements. Guidance: Include booking, vehicle size, routes, banksmen, lifting, loading limits and protection of public areas.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

D4 ¦ SITE LOGISTICS AND ACCESS. Agree segregation and protection of building users. Guidance: Confirm barriers, temporary routes, escape paths, dust, noise, vibration, signage and communication.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

D5 ¦ SITE LOGISTICS AND ACCESS. Agree housekeeping, waste and cleaning standards. Guidance: Define who keeps shared routes clear, how waste is removed and the standard required before areas are returned.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

D6 ¦ SITE LOGISTICS AND ACCESS. Confirm temporary accommodation and decant readiness. Guidance: Check users, furniture, IT, records, equipment and services can move before the contractor needs the area.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

E1 ¦ SERVICES AND TEMPORARY WORKS. Confirm existing service locations and isolation controls. Guidance: Record drawings, verification, permits, authorised persons, notice periods, contingency and restoration testing.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

E2 ¦ SERVICES AND TEMPORARY WORKS. Agree temporary power, water, lighting, heating and drainage. Guidance: State source, capacity, metering, protection, maintenance and responsibility for cost.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

E3 ¦ SERVICES AND TEMPORARY WORKS. Review temporary works management. Guidance: Identify design, checking, coordination, permits, inspections and responsibilities for scaffolds, propping, hoardings and excavations.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

E4 ¦ SERVICES AND TEMPORARY WORKS. Confirm fire precautions during construction. Guidance: Address escape routes, alarms, hot work, compartment breaches, fire loading, extinguishers, temporary detection and liaison with the client fire strategy.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

E5 ¦ SERVICES AND TEMPORARY WORKS. Confirm weather protection and protection of existing fabric. Guidance: Include roofs, openings, heritage finishes, occupied areas, stored items and emergency response to water ingress.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

F1 ¦ QUALITY AND INFORMATION. Confirm the contractor is using the correct drawings and specifications. Guidance: Establish the controlled issue process and remove superseded information from use.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

F2 ¦ QUALITY AND INFORMATION. Agree submittal, sample and approval schedules. Guidance: Record what requires review, lead times, decision authority and the consequence of procurement before approval.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

F3 ¦ QUALITY AND INFORMATION. Agree inspection, test and quality plans. Guidance: Identify hold points, witness points, records, benchmarks, mock-ups and responsibility for correcting non-conforming work.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

F4 ¦ QUALITY AND INFORMATION. Agree meeting and reporting arrangements. Guidance: Set frequency, attendees, agenda, minutes, progress data, photographs, risk, cost and programme reporting.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

F5 ¦ QUALITY AND INFORMATION. Agree request-for-information and design-query routes. Guidance: Record response times, priorities, document control and escalation of unanswered matters.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

G1 ¦ COMMERCIAL CONTROLS. Confirm payment procedures and valuation dates. Guidance: Align contractor applications, site review, certification, invoices and client payment approvals with the contract.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

G2 ¦ COMMERCIAL CONTROLS. Agree change-control and variation procedures. Guidance: No informal instruction should create unrecorded cost. Define request, quotation, impact assessment, authority and instruction.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

G3 ¦ COMMERCIAL CONTROLS. Confirm the current budget, risk allowance and forecast process. Guidance: Set reporting format for approved changes, anticipated changes, claims, contingency and forecast final cost.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

G4 ¦ COMMERCIAL CONTROLS. Agree records for delay, disruption and loss-and-expense events. Guidance: Use early warnings, notices, programme evidence, instructions and contemporaneous records as required by the contract.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

H1 ¦ COMMISSIONING AND HANDOVER. Agree the commissioning strategy and programme. Guidance: Identify systems, specialists, witness requirements, seasonal testing, records and client attendance.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

H2 ¦ COMMISSIONING AND HANDOVER. Agree O&M, as-built, asset and health-and-safety-file requirements. Guidance: Set formats, templates, review dates and progressive delivery rather than leaving all documents until completion.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

H3 ¦ COMMISSIONING AND HANDOVER. Agree training and familiarisation requirements. Guidance: Identify trainees, systems, dates, materials, recordings and repeat sessions needed before occupation.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

H4 ¦ COMMISSIONING AND HANDOVER. Agree practical-completion and handover criteria. Guidance: Define inspections, documentation, testing, cleaning, keys, statutory evidence, defects and client-readiness requirements.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

H5 ¦ COMMISSIONING AND HANDOVER. Agree aftercare and defects-period contacts. Guidance: Record response routes, emergency cover, access arrangements and planned reviews after occupation.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

I1 ¦ START DECISION. List every action that must be completed before work starts. Guidance: Separate genuine stop items from actions that can be closed shortly after mobilisation.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

I2 ¦ START DECISION. Confirm site readiness through a joint inspection. Guidance: Check boundaries, access, welfare, protection, isolation, temporary routes and areas to be handed over.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

I3 ¦ START DECISION. Record the formal start decision and any conditions. Guidance: Use Approved, Approved subject to actions or Not approved. Name the authority and evidence.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

I4 ¦ START DECISION. Issue the meeting record promptly. Guidance: Include decisions, actions, owners and dates and obtain corrections before the contractor relies on it.. STATUS [ ] Not reviewed [ ] Complete [ ] Action required [ ] Risk accepted [ ] N/A. EVIDENCE / DECISION / NOTES ________________________________________________________________________________________________________ ________________________________________________________________________________________________________. ACTION REQUIRED / NEXT STEP ________________________________________________________________________________________________________. Owner ____________________________; Due date ____________________________; Date closed ____________________________..

STAGE GATE DECISION

Gate test

The contractor may start only when stop items are closed or formally controlled, and every unresolved action has an owner and due date.

Decision

[ ] Approved to proceed [ ] Approved with conditions [ ] Do not proceed [ ] Review not yet completed

Approved by ______________________________________________; Date ______________________________________________.

Conditions, exceptions and residual risks

Record every condition or accepted exception, together with its owner and completion date where relevant. ________________________________________________________________________________________________________ ________________________________________________________________________________________________________ ________________________________________________________________________________________________________ ________________________________________________________________________________________________________ ________________________________________________________________________________________________________ ________________________________________________________________________________________________________ ________________________________________________________________________________________________________

Building Project Checklists — expanded downloadable resource | Version 1.0, 22 July 2026. For client-side project governance. Confirm current legislation, contract terms, organisational procedures and project-specific professional advice.