# Practical Completion Checklist

Companion working resource for Building Contract Administration in Practice

| Project / organisation |  | Prepared by |  |
| --- | --- | --- | --- |
| Version | 1.0 | Issue date | 8 September 2026 |

Purpose: Supports a structured inspection and evidence review before the Contract Administrator decides whether the contractual test for Practical Completion has been met.

Certification decision

Practical Completion is a certification decision under the contract. This checklist supports that judgement but does not create a separate test or permit certification subject to substantial incomplete work.

# Inspection details

| Project / section |  |
| --- | --- |
| Contract form, edition and clause |  |
| Date for Completion |  |
| Inspection date |  |
| Contractor attendees |  |
| Client / consultant attendees |  |
| Proposed certification date |  |
| Outstanding-information deadline |  |

# 1. Works and quality

| Ref | Check / action | Evidence / response | Owner / date | Status |
| --- | --- | --- | --- | --- |
| 1.1 | The works or section are complete for their intended use, subject only to minor residual items compatible with the contractual test. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 1.2 | No material element remains incomplete, unsafe, unusable or dependent on temporary arrangements. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 1.3 | Testing, commissioning, demonstrations and witnessing are complete with acceptable results. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 1.4 | Statutory approvals, inspections and certificates required for occupation or use are available. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 1.5 | Fire stopping, compartmentation, life-safety systems and escape arrangements are complete and evidenced. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 1.6 | Cleaning, making good, protection removal and waste clearance are satisfactory. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 1.7 | Snagging has not been used to conceal substantive incomplete or defective work. |  |  | ☐ Open ☐ Complete ☐ N/A |

# 2. Handover and operation

| Ref | Check / action | Evidence / response | Owner / date | Status |
| --- | --- | --- | --- | --- |
| 2.1 | Operating and maintenance information sufficient for safe use is available. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 2.2 | Training and demonstrations have been delivered to the correct operational staff. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 2.3 | Keys, access controls, passwords, licences, spares, tools and consumables are handed over. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 2.4 | As-built drawings, asset data and commissioning records are received to the agreed status. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 2.5 | Emergency, shutdown, isolation and call-out arrangements are understood. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 2.6 | Insurance, security, utilities and operational ownership changeovers are ready. |  |  | ☐ Open ☐ Complete ☐ N/A |

# 3. Contract and commercial consequences

| Ref | Check / action | Evidence / response | Owner / date | Status |
| --- | --- | --- | --- | --- |
| 3.1 | Any sectional completion, partial possession or early-use arrangements are correctly distinguished. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 3.2 | The effect on liquidated damages / delay damages is recorded. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 3.3 | Retention release and payment consequences are diarised. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 3.4 | The rectification period / defects date and reporting route are confirmed. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 3.5 | Outstanding warranties, bonds, approvals or documents are risk assessed and controlled. |  |  | ☐ Open ☐ Complete ☐ N/A |
| 3.6 | The certificate wording, date and distribution comply with the contract. |  |  | ☐ Open ☐ Complete ☐ N/A |

# Decision record

| Decision | Certify / Do not certify / Further inspection required. |
| --- | --- |
| Reasons and contractual basis |  |
| Minor outstanding items | Reference controlled schedule only. |
| Required evidence before issue |  |
| Certificate reference and date |  |
| Authorised signatory |  |
| Distribution and diary actions |  |

Important use note

This document is a practical working template, not legal, contractual or technical advice. Adapt it to the project, organisation, executed contract, amendments, applicable law and competent-person advice. Retain supporting evidence and record why any item is marked not applicable.

Ink & Lintel | Version 1.0 | 8 September 2026